## Slide 1
EMERGENCY SUPPLY CHAIN PLAYBOOK
Response Quick Guide

## Slide 2
PEOPLE AND PROCESSES
RESPONSE QUICK GUIDE
GOVERNANCE AND ORGANIZATION
ESC Lead
Week 1, Ongoing
Establish liaisons mechanisms with the relevant focal points from the ESC support network (sectoral, regional, partners), to share information regarding the situation on the ground and the areas of support of each stakeholder
Conduct initial meetings with the EOC Team to gather information on the crisis
EOC Coordinator
Day I
ESC Lead
Day 1
Convene the ESC team to develop initial response plan
ESC Lead
Ongoing
Contact, via the relevant regional ESC focal points, all regional and local technical staff involved in supply chain to communicate response plan and coordinate the logistics on the ground
ESC Lead
After containment of emergency
Coordinate demobilization of resources that have been deployed on the ground
ESC Lead
Week 1, Ongoing
Plan and update emergency supply chain response with all the relevant focal points from the ESC support network
Identify the key stakeholders from the ESC support network to involve in the response
ESC Lead, with support of the ESC Branch
Day 1, Ongoing
ESC Lead
End of emergency
Conduct after-action review with the EOC, the ESC Core team, and all the ESC support network to determine key changes to preparedness, response, and training activities
ACTION
RESPONSIBLE
TIME FRAME

## Slide 3
people and processes
RESPONSE QUICK GUIDE
TRIGGERS
Liaison Officer
Day 1
Alert the relevant Ministries and International Partners
The EOC Planification and Operation Sections
Day 1, Ongoing
Review the risk analysis with the input from the evolution of the epidemic, in order to update the estimation of potential cases and high-risk geographical areas
Incident Manager
End of emergency
Declare the end of the sanitary crisis
The EOC Planification Section, the ESC Lead
End of emergency
Update the ‘Disease Prioritization’ tracker of the Playbook with new information regarding the disease profiles and re-evaluate the risk assessment
EOC Coordinator
Day 1
Activate the EOC, nominate the Incident Manager and activate the response mode of the ESC team as soon as the alert threshold is reached
The EOC Planification section
Day 1, Ongoing
Elaborate a template of Situation Report to be used daily for the debrief of the epidemiologic situation
ACTION
RESPONSIBLE
TIME FRAME

## Slide 4
PEOPLE AND PROCESSES
RESPONSE QUICK GUIDE
EOC Finance & Admin, ESC Lead, EOC Command
Week I
Access owned (MoPH) and external funding mechanisms by submitting necessary applications
EOC Finance & Admin,
ESC Lead
Week 1
Estimate funds required to respond to emergency based on updated risk assessment
FINANCING
Week I, Ongoing
Activate documentation protocols listed for funding mechanism access and record all expenses in adherence to funding mechanism requirements
EOC Finance & Admin,
ESC Lead
Work with the Procurement team of the EOC Logistics function to activate the emergency processes to suspend the requirements for multiple quotes and public bidding
Week I, Ongoing
EOC Finance & Admin,
Procurement team
Document and update the ‘Response Funding Mechanisms’ tracker in the Playbook, with the lessons learned from the crisis
End of emergency
EOC Finance & Admin
Immediately process payments due to vendors, as any delay in payments might hinder the delivery of goods.
Week I, Ongoing
EOC Finance & Admin,
Procurement team
ACTION
RESPONSIBLE
TIME FRAME

## Slide 5
DATA VISIBILITY
Hold bi-weekly calls from national to regional, regional to local to gather stock levels of identified “indicator” commodities
ESC Lead
Ongoing
PEOPLE AND PROCESSES
RESPONSE QUICK GUIDE
ESC Lead
Day 1
Identify the key datasets to be tracked and updated on a daily and/or weekly basis: stock levels of identified indicator commodities, consumption rates, procurement orders, re-supply needs
ESC Lead
End of Emergency
Reconvene and follow up with ESC Team to ensure all databases, response protocols, and reporting have been documented and updated according to lessons learned from the emergency, and making it accessible to other stakeholders.
Ongoing
Ensure that consumption rate of key “tracker” commodities are updated bi-weekly
ESC Lead
Ensure that consumption data are shared with Procurement Lead to inform re-supply
Ongoing
ESC Lead
ACTION
RESPONSIBLE
TIME FRAME

## Slide 6
COMMODITY FORECASTING
COMMODITY PLANNING
RESPONSE QUICK GUIDE
EOC Operations Section
Identify necessary commodities based on disease specifications and commodities database, confirming with experts, and determine “indicator” commodities
Day 1
Use the ‘Response Scenario’ tracker to forecast initial quantities required depending on the type of outbreak (disease, number of projected cases)
Day I
EOC Operations Section
Communicate quantities to the Logistics Lead, for him to (i) let the Stockpile team know which quantity from which stockpile he needs to mobilize and (ii) enable the Logistics and Transport team to prepare properly real estate and transport options
Week 1
EOC Operations Section
If necessary, adjust the forecasted quantities by modifying the ‘Response Scenario’ tracker, with the input from the medical leads in charge of following-up on the evolution of the sanitary situation
Week 1, Ongoing
EOC Operations Section
ACTION
RESPONSIBLE
TIME FRAME
Update the ‘Disease Job Aids’ and the ‘Commodities Database’ tracker to document any modifications in the commodities list
End of emergency
ESC Planification Team
Convene the EOC Operations Section to validate the forecasted quantities and make any adjustment, if necessary
Day 2, Ongoing
EOC Operations Section

## Slide 7
PROCUREMENT
AND SOURCING
COMMODITY PLANNING
RESPONSE QUICK GUIDE
Procurement team
Identify the needs for procurement, based on the gap between the input from the EOC Planification section and the Stockpiling team
Day 1
Procurement team
Provide suppliers with necessary customs protocols to follow
Week 1
Maintain clear documentation of all steps in the procurement process, including inspection and documentation of goods received
Procurement team
Week 1, Ongoing
Increase limits of approval and authorization and checks signatory limits for purchases
Procurement team
Week 1, Ongoing
Suspend the requirement for multiple quotes, public bidding procedures and authorize single source purchase
Procurement team
Week 1, Ongoing
Procurement team
Refer to the ‘International Partners Sourcing Database’ to mobilize the remaining commodities among international partners in case of capacity gap with the suppliers
Day 2
Work with suppliers to identify any potential gaps or bottlenecks, in terms of available quantities and supplying delays
Procurement team
Day 2, Ongoing
Update the ‘Procurement Database’ tracker in the playbook, to document any additional information that you gathered on suppliers
Procurement team
End of crisis
Procurement team
Get input from the EOC Planification section regarding the list of commodities required and their quantities
Day 1
Procurement team
Reach out to the Stockpiling team to know which quantities of which commodities they can supply
Day 1
Procurement team
Contact all suppliers identified in “Supplier Database” to activate agreements and order the adequate quantities
Day 1
ACTION
RESPONSIBLE
TIME FRAME

## Slide 8
STOCKPILING
COMMODITY PLANNING
RESPONSE QUICK GUIDE
ESC Lead, Stockpiling team
Contact stockpile managers to approve release stockpiles of necessary commodities
Day I
Stockpiling team
Calculate how long stockpile will be sufficient for to determine resupply needs
Week 1
Stockpiling team, Logistics & Transport team
Move stocks from stockpile to pre-positioning site
Day I
Logistics & Transport team
Update stock levels in information management system
Ongoing
Procurement team
Resupply stockpile according the stockpiling strategy
After outbreak
Procurement team
Update the stockpiling strategy if necessary (e.g. modify the number of months to stockpile, the levels of stockpiling)
After outbreak
ACTION
RESPONSIBLE
TIME FRAME

## Slide 9
WAREHOUSING
AND STORAGE
LOGISTICS AND TRANSPORT
RESPONSE QUICK GUIDE
ACTION
RESPONSIBLE
Logistics & Transport tam
If necessary, set up temporary warehousing in pre-identified sites
Ongoing
Logistics & Transport team, ESC Lead
Institute security at all storage sites, especially for temporary warehousing, under the coordination of MINATD
Ongoing
Logistics & Transport team, ESC Lead
Mobilize additional warehousing staff by reaching out to contacts on Warehousing and Storage database
Week I, Ongoing
TIME FRAME
Logistics & Transport team
Follow-up on notification of reception of response - by all communication means
Ongoing
Logistics & Transport team
Update database of temporary storage locations by adding or removing locations in accordance with effectiveness and compliance as lessons learned from the emergency
End of emergency
Logistics & Transport team
Call identified permanent & temporary warehousing and storage contacts to share emergency response plan and ensure they are properly preparing capacity (e.g., clearing waste and designating emergency storage space) and get their available capacity
Day I, Ongoing
ESC Lead
If necessary, reach out to the Governor to requisition any additional warehousing and storage in his region
Week I, ongoing
Logistics & Transport team
Identify the relevant permanent and temporary storage and warehouses to use, depending on their geographical location, their capacity characteristics (e.g. cold chain)
Day I, Ongoing
Logistics & Transport team
With the input from the EOC Planification Section, estimate the storage capacity requirements and the storage capacity gap with the help of the ‘Volume requirements calculation tracker’
Day I, Ongoing
Logistics & Transport team
Reference the usable storage and warehouses as well as their available capacity in the ‘Permanent Storage Database’ and the ‘Temporary Storage Database’
Day I, Ongoing

## Slide 10
TRANSPORT AND WASTE MANAGEMENT
TRANSPORT AND LOGISTICS
RESPONSE QUICK GUIDE
Ongoing
Logistics & Transport team
Activate contracts with identified transport contacts (e.g. freight forwarders, third-party logistics provider)
Ongoing
Logistics & Transport team, EOC Safety Officer
Institute disease-specific safety protocols for transport and waste management (with medical input from the Medical Section)
Day 1
Logistics & Transport team
Activate coordination mechanisms with other relevant sectors (e.g. Ministry of Transport, Ministry of Defense, etc) to help unload cargo at airport/seaports
Logistics & Transport team
Day I, Ongoing
Prepare the distribution plan based on the needs expressed by the planning section and procurement leads
Day I
Logistics & Transport team
Contact Customs office to activate agreements for expedited goods
Institute security protocols, in coordination with MINADT, to secure transport depending on the security risk of the region
Ongoing
ESC Lead
Logistics & Transport team
Ongoing
Follow-up on notification of delivery or any distribution delays - by all communication means
Ongoing
Logistics & Transport team
Share distribution plan with all transporters, including key performance indicators and objectives
After the containment
Logistics & Transport team
Conduct demobilization and waste management in coordination with MINEDPED, according to the procedures and considerations based on waste categorization and disposal best practices
End of Emergency
Logistics & Transport team
Update database of transport options and waste disposal sites by adding or removing information or locations in accordance with lessons learned from the emergency
ACTION
RESPONSIBLE
TIME FRAME